## New Issues
USER LOGIN
BUGS
Date format to be DD/MM/YYYY on all screens.
In 'New User Registration' when the user enters an Incorrect Captcha, all fields shouldn't get cleared. Also there has to be a functional option of 'Refresh Captcha'. Also Change the captcha style itself. Too difficult to get right. Error Message to be - 'Incorrect Captcha! Please try again.'
During 'New User Registration', does checking of 'receive mails ' checkbox update flag in backend. Need to check this. These mails Ids will be used in future for newletters.
Not filling in mandatory fields in 'New User Registration' goes to a messy page. Check of mandatory fields happening, but display is messy.
In 'New Function Booking' it allows function booking for previous dates also. This should not be allowed!!
In 'New Function Booking' mandatory fields check not happening in Booking Details for Function.
IN 'Function Booking Payment successful' page - the confirmation msg. should dynamically display that specific functions details (as mentioned in the shared document). Also, add a button -> Click to Order Platters (as mentioned in the shared document)
If a user has more than 1 function booked, the platter selection shows the same instance for all the functions.
In 'Platter Selection' required Pop-ups don't display on adding Platter to Cart. Also Pop-ups for 'Clear Cart' are not working. Check shared document for reference.
In the success message after a 'Platter Booking', the confirmation msg. should dynamically display the specific functions details (as mentioned in the shared document).
Cancellation of PAYPAL payment for Platters in 'Platter Booking' still adds it to UNPAID PLATTERS tables. It shouldn't do that. It has to be a failed transaction.
Successful payment through PAYPAL for Platters in 'Platter Booking' adds it to UNPAID PLATTERS and not to PAID PLATTERS.
'Platter Order History' page should have details of all placed orders by a user with function date. The page is empty even after I've confirmed & paid for orders.
Mails need to be sent for successful Platter Booking. Mails also need to be sent for unpaid Platters 10 days before, 8 days before and 7 days before the function.This is happening, but needs to cross-checked for consistency.
If you are killing a Session after sometime of inaction, the page has to say it. Now it simply stops connecting to database which misleads a customer.
The 'From' Name & Email to be changed for auto-generated emails.
'Back' in 'New User Registration' should take user to Log-in page.
Grey out 'Email id' on all screens.
In 'Platter Booking' introductory page, image for 'Proceed to book platter orders' is image being picked from 'Hot Platters' category details in the backend. It should be a standalone separate image.
In 'Platter Booking' - 'Item Selection', we cannot shift between HOT & COLD Platters when spelling/case of Hot/Cold platters is changed in backend. Platter item validation for Hot or cold also fails when this is done.
When user logs in with a mail id already existing in Database the message is 'This Email-id Is Already Registered try With Another'. Change to 'This Email-id is already registered with us.'
in 'Function Bookings', when the user has no bookings, text to be - You have no Bookings currently! . Currently, the text reads 'Your Current Bookings are empty'
In the Function Bookings result table, change the text under the columns 'Time' to 'Lunch' & 'Dinner' (it is currently 'dinner' & 'lunch')
Payment failure screen -> Text to be exactly as below. The 2nd line to be in BOLD. Sorry, but processing of your Payment has failed! Please contact us at 33963824 or info@manlydeck.com.au
In the GREEN navigation buttons on top, we might have to change the color of the text of the current page to WHITE, as that makes it easier for the user to identify the page. This holds for navigation 2nd Level down also. Else we won't know what page of navigation we are on.
Link verification screen to be created. Text for the screen --> Your account has now been activated! Please login and proceed to book your function. [Provide Login input fields (same as Login screen) in the same screen]
ADMIN LOGIN
BUGS
Date format to be DD/MM/YYYY on all screens.
In 'Function Booking', booking of a function by admin without filling mandatory fields, does a successful booking but goes to a page with lot of error msgs. Same case with all fields filled in. The above wrong booking also fires mail. Validation for email also needs to be done here.
Admin end user registration. Welcome mail should be sent to user. It should have username and pswd and should be activated also!! But when should this be?? Should the account created be pre-activated?? So user only needs to login and change pswd.
In 'Function Booking' mail should be fired for successful booking of function by admin on behalf of a user.
In 'Current Booking' pagination doesn't seem to work. Also 'Time' (Slot) is missing from results column.
In 'Past Bookings' 'Time' (Slot) is missing from results column.
Go to 'Deck Area Prices'. Then Navigate to 'Booking Calendar'. It goes into Client Side UI . Don't know if it was a session issue or something else. Couldn't replicate. Please check this.
In 'Paid Platter Orders' use the shared document as reference for columns & titles. In the modify section (Edit Paid Customer), make all the fields except for 'Platter Combination' non-editable. Also, change title of the page to 'Modify Platter'. Add 'Cancel' button to the screen.
In 'Unpaid Platter Orders', use the shared document as reference for columns & titles. Check table width. In the modify section (Edit Paid Customer), make all the fields except for 'Platter Combination' & 'Status' non-editable. Also, change title of the page to 'Modify Platter'. Add 'Cancel' button to the screen.
Delete of Paid & Unpaid Platters goes to last page of respective tables. Which is not right.
Changing of Platter Details does not work well. When you click MODIFY, the records table shows quantity taken from another place. Hence anything added in MODIFY after the '-' is not shown.
' Paid Platter' allows change of Status. This should not be allowed.
Font of 'What Do You Want To Manage' at top left to be the same as the headings in the User login section
In the 'Plater Categories', the image field should NOT be mandatory. Can even be removed if needed.
In the 'Platter Items' updation screen, display proper error msgs/warning for mandatory fields check. Currently its throwing a PHP error.
In the GREEN navigation buttons on top, we might have to change the color of the text of the current page to WHITE, as that makes it easier for the user to identify the page. This holds for navigation 2nd Level down also. Else we won't know what page of navigation we are on.